## overheadContribution
ContractNumber | GrossSubContractors | MovementSubContractors | GrossMaterials | MovementMaterials | GrossConsultants | MovementConsultants | GrossStats | MovementStats | GrossPreliminaries | MovementPreliminaries | GrossOthers | MovementOthers | GrossOHP | MovementOHP | GrossTotal | MovementTotal
C2356 | -1476036.05 | -343006 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## valueInformation
ContractNumber | CumulativeValueGross | CumulativeProfitGross | MonthlyValue | MonthlyProfit | QtrTurnOverMonthForeCast | QtrProfMonthForeCast | QtrTurnOverCumActual | QtrProfCumForecast | QtrProfCumActual | QtrTurnOverCumForeCast | PercentageCompleteTime | PercentageCompleteValue | AdherenceTarget | AdherenceActual
C2356 | 35526000 | 953999.0761 | 1931124 | 102493.6592 | 1614193.16 | 60000 | 1931124 | 25000 | -30000.2261 | 1614193.16 | 82.21% | 77.81% | 5700432 | 6051079.75

## projectKPIs
ContractNumber | AdherenceTgtPct | AdherenceTarget | AdherenceActual | MonthlyCashFlowPredTgtPct | QtrCashFlowPredTgtPct | NonRecWorksTgtPct | NonRecWorksActPct | NonRecoverableWorks | PredOfProgramme | PredOfProgrammeAct | HAuditScoreTgtPct | HSAuditScotAct | HSAccidentIncidentRateTgtPct | HSAccidentIncidentRateActPct | PctRecycledWasteTgt | PctRecycledWasteAct
C2356 | 100 | 5700432 | 6051079.75 | 105 | 105 | 1 | 0.019381 | 477228 | 0 | 0 | 80 | 6.164 | 0.57011 | 0.66952 | 90 | 98

## timeValue
ContractNumber | ConCompDate | EstCompDate | WeeksCompleted | WeeksContracted | TimeCompleted | TimeRemaining | ValueCompleted | ValueRemaining
C2356 | 9 May 2018 | 2018-10-30 | 134 | 163 | 82.2086 | 17.7914 | 98.2739 | 1.7261

## NewRecordOfLabour
ContractNumber | WeekNum | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
C2356 | 17 | 40 | 39 | 40 | 0 | 36 | 0 | 0
C2356 | 18 | 32 | 33 | 34 | 36 | 34 | 0 | 0
C2356 | 19 | 32 | 33 | 34 | 36 | 34 | 0 | 0
C2356 | 20 | 17 | 24 | 21 | 27 | 23 | 13 | 0
C2356 | 21 | 17 | 22 | 20 | 25 | 21 | 12 | 0
C2356 | 22 | 23 | 25 | 23 | 23 | 22 | 0 | 0
C2356 | 23 | 17 | 21 | 19 | 18 | 16 | 0 | 0
C2356 | 24 | 0 | 17 | 19 | 20 | 17 | 0 | 0
C2356 | 25 | 17 | 20 | 18 | 18 | 19 | 0 | 0
C2356 | 26 | 17 | 18 | 19 | 23 | 20 | 0 | 0
C2356 | 27 | 21 | 22 | 21 | 20 | 14 | 0 | 0
C2356 | 28 | 16 | 17 | 14 | 17 | 15 | 0 | 0
C2356 | 29 | 12 | 13 | 13 | 17 | 17 | 0 | 0
C2356 | 30 | 15 | 14 | 14 | 17 | 15 | 0 | 0
C2356 | 31 | 13 | 14 | 14 | 14 | 14 | 0 | 0
C2356 | 32 | 13 | 14 | 14 | 14 | 14 | 0 | 0
C2356 | 33 | 14 | 15 | 11 | 11 | 15 | 0 | 0
C2356 | 34 | 13 | 14 | 14 | 14 | 13 | 0 | 0
C2356 | 35 | 9 | 18 | 15 | 15 | 17 | 0 | 0
C2356 | 36 | 14 | 15 | 12 | 14 | 14 | 2 | 0
C2356 | 37 | 14 | 17 | 14 | 17 | 13 | 0 | 0
C2356 | 38 | 16 | 14 | 15 | 21 | 19 | 0 | 0
C2356 | 39 | 24 | 24 | 21 | 22 | 0 | 0 | 0
C2356 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C2356 | 41 | 13 | 14 | 14 | 14 | 14 | 0 | 0
C2356 | 42 | 14 | 15 | 11 | 11 | 15 | 0 | 0
C2356 | 43 | 13 | 14 | 14 | 14 | 13 | 0 | 0
C2356 | 44 | 9 | 18 | 15 | 15 | 17 | 0 | 0
C2356 | 45 | 18 | 18 | 18 | 22 | 21 | 0 | 0
C2356 | 46 | 196 | 16 | 13 | 17 | 17 | 0 | 0
C2356 | 47 | 19 | 22 | 24 | 23 | 22 | 0 | 0
C2356 | 48 | 24 | 27 | 26 | 28 | 25 | 0 | 0
C2356 | 49 | 28 | 34 | 33 | 33 | 27 | 0 | 0
C2356 | 50 | 35 | 37 | 33 | 29 | 33 | 0 | 0
C2356 | 51 | 23 | 31 | 29 | 27 | 24 | 0 | 0
C2356 | 52 | 26 | 27 | 30 | 20 | 22 | 0 | 0
C2356 | 53 | 25 | 24 | 25 | 20 | 1 | 0 | 0
C2356 | 54 | 1 | 29 | 29 | 29 | 29 | 1 | 1
C2356 | 55 | 28 | 30 | 27 | 29 | 37 | 1 | 1
C2356 | 56 | 40 | 39 | 40 | 42 | 43 | 1 | 1
C2356 | 57 | 46 | 45 | 44 | 49 | 50 | 1 | 1
C2356 | 58 | 48 | 48 | 46 | 46 | 46 | 1 | 1
C2356 | 59 | 1 | 54 | 51 | 52 | 54 | 1 | 1
C2356 | 60 | 56 | 55 | 55 | 57 | 55 | 1 | 1
C2356 | 61 | 59 | 60 | 62 | 65 | 68 | 1 | 1
C2356 | 62 | 66 | 66 | 64 | 63 | 47 | 1 | 1
C2356 | 63 | 1 | 84 | 85 | 87 | 87 | 1 | 1
C2356 | 64 | 91 | 91 | 78 | 82 | 81 | 1 | 1
C2356 | 65 | 68 | 73 | 72 | 78 | 73 | 1 | 1
C2356 | 66 | 16 | 78 | 87 | 84 | 84 | 1 | 1
C2356 | 67 | 89 | 90 | 85 | 78 | 73 | 1 | 1
C2356 | 68 | 92 | 92 | 89 | 85 | 85 | 1 | 1
C2356 | 69 | 81 | 82 | 82 | 83 | 83 | 1 | 1
C2356 | 70 | 81 | 84 | 85 | 86 | 86 | 1 | 1
C2356 | 71 | 78 | 81 | 82 | 85 | 79 | 0 | 0
C2356 | 72 | 78 | 81 | 82 | 85 | 79 | 0 | 0
C2356 | 73 | 79 | 83 | 90 | 77 | 75 | 1 | 1
C2356 | 74 | 83 | 84 | 82 | 86 | 89 | 0 | 0
C2356 | 75 | 94 | 95 | 95 | 98 | 88 | 1 | 1
C2356 | 76 | 1 | 90 | 99 | 101 | 96 | 1 | 1
C2356 | 77 | 99 | 100 | 103 | 101 | 101 | 1 | 1
C2356 | 78 | 104 | 112 | 117 | 118 | 107 | 0 | 0
C2356 | 79 | 111 | 114 | 114 | 115 | 113 | 1 | 1
C2356 | 80 | 116 | 116 | 116 | 110 | 116 | 1 | 1
C2356 | 81 | 109 | 114 | 109 | 111 | 107 | 0 | 0
C2356 | 82 | 101 | 101 | 100 | 100 | 102 | 0 | 0
C2356 | 83 | 95 | 104 | 108 | 108 | 105 | 1 | 1
C2356 | 84 | 103 | 110 | 117 | 110 | 109 | 1 | 1
C2356 | 85 | 119 | 118 | 114 | 117 | 119 | 1 | 1
C2356 | 86 | 121 | 124 | 123 | 127 | 128 | 1 | 1
C2356 | 87 | 127 | 123 | 124 | 123 | 123 | 1 | 1
C2356 | 88 | 115 | 120 | 113 | 123 | 118 | 1 | 1
C2356 | 89 | 129 | 129 | 125 | 122 | 125 | 1 | 1
C2356 | 90 | 122 | 121 | 128 | 121 | 122 | 1 | 1
C2356 | 91 | 116 | 119 | 119 | 119 | 117 | 1 | 1
C2356 | 92 | 107 | 105 | 102 | 5 | 3 | 1 | 1
C2356 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C2356 | 94 | 2 | 8 | 77 | 79 | 79 | 1 | 1
C2356 | 95 | 58 | 92 | 100 | 103 | 96 | 1 | 1
C2356 | 96 | 109 | 114 | 119 | 111 | 111 | 1 | 1
C2356 | 97 | 109 | 109 | 113 | 111 | 108 | 98 | 1
C2356 | 98 | 114 | 115 | 114 | 111 | 115 | 0 | 0
C2356 | 99 | 104 | 115 | 114 | 113 | 111 | 1 | 1
C2356 | 100 | 108 | 107 | 111 | 104 | 105 | 1 | 1
C2356 | 101 | 119 | 123 | 122 | 128 | 125 | 1 | 1
C2356 | 102 | 129 | 126 | 130 | 129 | 131 | 1 | 1
C2356 | 103 | 131 | 139 | 138 | 129 | 128 | 1 | 1
C2356 | 104 | 139 | 135 | 135 | 140 | 140 | 1 | 1
C2356 | 105 | 162 | 162 | 157 | 161 | 157 | 1 | 1
C2356 | 106 | 149 | 147 | 147 | 149 | 149 | 1 | 1
C2356 | 107 | 149 | 152 | 148 | 149 | 145 | 2 | 1
C2356 | 108 | 132 | 131 | 131 | 126 | 1 | 1 | 1
C2356 | 109 | 1 | 126 | 130 | 128 | 131 | 1 | 1
C2356 | 110 | 138 | 136 | 138 | 134 | 139 | 1 | 1
C2356 | 111 | 1 | 123 | 121 | 117 | 112 | 2 | 1
C2356 | 112 | 137 | 138 | 141 | 138 | 139 | 1 | 1
C2356 | 113 | 123 | 124 | 126 | 123 | 124 | 0 | 0
C2356 | 114 | 126 | 127 | 127 | 123 | 125 | 0 | 0
C2356 | 115 | 0 | 130 | 130 | 130 | 133 | 0 | 0
C2356 | 116 | 107 | 107 | 108 | 109 | 111 | 0 | 0
C2356 | 117 | 117 | 117 | 114 | 113 | 114 | 0 | 0
C2356 | 118 | 98 | 105 | 103 | 101 | 101 | 2 | 0
C2356 | 119 | 104 | 104 | 105 | 102 | 103 | 0 | 0
C2356 | 120 | 98 | 101 | 98 | 98 | 98 | 0 | 0
C2356 | 121 | 101 | 98 | 98 | 97 | 98 | 0 | 0
C2356 | 122 | 101 | 98 | 98 | 97 | 98 | 0 | 0
C2356 | 123 | 101 | 98 | 98 | 97 | 98 | 0 | 0
C2356 | 124 | 105 | 104 | 106 | 105 | 103 | 16 | 0
C2356 | 125 | 102 | 101 | 102 | 103 | 102 | 2 | 0
C2356 | 126 | 108 | 108 | 106 | 106 | 101 | 0 | 0
C2356 | 127 | 99 | 100 | 101 | 101 | 103 | 0 | 0

## monthlyKPI
ContractNumber | Date | TtlSkipWasteM3 | TtlCartAwayWasteM3 | SkipWasteRecycled | WaterM3 | emitFromDieselKgCo2 | EmitFromElectrictyKgCo2 | TtlEmitkgCO2 | Wstper100kM3 | emitFromEnergyKgCo2Per100k | waterM3Per100k | ActualTO | All Skip waste m3
C2356 | 2015-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | All cart away waste m3
C2356 | 2015-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296169 | % Skip Waste recycled
C2356 | 2015-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562619 | Water m3
C2356 | 2015-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 711400 | Emissions from Diesel kgCO2
C2356 | 2015-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492586 | Emissions from Electricty kgCO2
C2356 | 2015-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1090619 | Total Emissions kgCO2
C2356 | 2015-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595500 | Waste per £100k m3
C2356 | 2015-11-01 | 0 | 0 | 0 | 0 | 0 | 7802.4 | 7802.4 | 0 | 1541.367 | 0 | 506200 | Emissions from Energy kgCO2 per £100k
C2356 | 2015-12-01 | 0 | 0 | 0 | 0 | 0 | 7152.2 | 7152.2 | 0 | 936.2744 | 0 | 763900 | Water m3 per £100k
C2356 | 2016-01-01 | 0 | 0 | 0 | 0 | 0 | 10143 | 10143 | 0 | 1717.9878 | 0 | 590400 | Actual T.O
C2356 | 2016-02-01 | 0 | 0 | 0 | 0 | 0 | 10143.12 | 10143.12 | 0 | 1170.18 | 0 | 866800 | No. Of Skips
C2356 | 2016-03-01 | 0 | 0 | 0 | 63.9 | 10143.12 | 0 | 10143.12 | 0 | 849.721 | 5.3531 | 1193700 | No of Yds
C2356 | 2016-04-01 | 0 | 0 | 0 | 34.37 | 9227 | 0 | 9227 | 0 | 943.7455 | 3.5154 | 977700 | M3
C2356 | 2016-05-01 | 12.24 | 5175 | 94 | 91 | 10454 | 192 | 10646 | 0.91316 | 794.2405 | 6.789 | 1340400 | Tonnes
C2356 | 2016-06-01 | 12.24 | 2430 | 94 | 82.01 | 5821 | 320 | 6141 | 0.75965 | 381.1305 | 5.0898 | 1611259 | Recycled %
C2356 | 2016-07-01 | 78 | 0 | 94 | 110.93 | 4764.7 | 143.9 | 4908.6 | 6.5461 | 411.9539 | 9.3098 | 1191541 | M3 Waste Diverted
C2356 | 2016-08-01 | 114 | 0 | 94 | 113 | 11651 | 2422.07 | 14073.07 | 14.8399 | 1831.9539 | 14.7097 | 768200 | Waste to Landfill
C2356 | 2016-09-01 | 189 | 0 | 94 | 120 | 12338 | 2703.17 | 15041.17 | 16.7517 | 1333.1499 | 10.636 | 1128243 | Waste Carrier
C2356 | 2016-10-01 | 192 | 0 | 94 | 146 | 13844 | 509 | 14353 | 16.5595 | 1237.9071 | 12.5921 | 1159457
C2356 | 2016-11-01 | 144 | 0 | 94 | 191 | 6803 | 829 | 7632 | 12.1982 | 646.5057 | 16.1796 | 1180500
C2356 | 2016-12-01 | 114 | 207 | 98 | 213 | 6367 | 1063 | 7430 | 7.9793 | 520.0532 | 14.9087 | 1428700
C2356 | 2017-01-01 | 24.48 | 189 | 98 | 231 | 5552 | 1045 | 6597 | 2.3319 | 628.4054 | 22.0042 | 1049800
C2356 | 2017-02-01 | 36.72 | 117 | 98 | 276 | 5988 | 1088 | 7076 | 2.6665 | 513.8334 | 20.0421 | 1377100
C2356 | 2017-03-01 | 116.28 | 180 | 98 | 229 | 6511 | 1127 | 7638 | 6.2712 | 411.9297 | 12.3503 | 1854200
C2356 | 2017-04-01 | 110.16 | 189 | 98 | 171 | 7232 | 2426 | 9658 | 6.5544 | 574.6415 | 10.1743 | 1680700

## progress
ContractNumber | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01
C2356 | 0 | -4 | 0 | -4.5 | 2 | 2 | 0 | 2 | 2 | 2 | 0 | -4 | -8 | -10 | -10 | -11.5 | -15.8 | -17 | -19.5 | -18 | -18 | -18 | -17.5 | -17.2

## financialData
ContractNumber | Column | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01
C2356 | CurrentCumTO | 250000 | 546169 | 1108788 | 1820188 | 2312774 | 3403393 | 3998893 | 4505093 | 5268993 | 5859393 | 6726193 | 7919893 | 8897593 | 10237993 | 11849252 | 13040793 | 13808993 | 14937236 | 16096693 | 17277193 | 18705893 | 19755693 | 21132793 | 22986993 | 24667693 | 26447493 | 28284093 | 29815893 | 31498393 | 33741893 | 35570093 | 37189093 | 38837093 | 40605093 | 42365093 | 44145093 | 45667093 | 47211093 | 48475093 | 49650393
C2356 | AcutalCumTO | 205907 | 502076 | 1064695 | 1776095 | 2268681 | 3359300 | 3954800 | 4461000 | 5224900 | 5815300 | 6682100 | 7875800 | 1064695 | 10193900 | 11805159 | 12996700 | 13764900 | 14893143 | 16052600 | 17233100 | 18661800 | 19711600 | 21088700 | 22942900 | 24623600 | 26403400 | 28240000 | 29771800 | 31454300 | 33697800 | 35526000 | 37145000 | 38793000 | 40561000 | 42321000 | 44101000 | 45623000 | 47167000 | 48431000 | 49606300
C2356 | OriginalCumTO | 250000 | 546169 | 1108788 | 1820188 | 2312774 | 3406393 | 3998893 | 4505093 | 5268993 | 5730993 | 6522993 | 7531993 | 8702993 | 9922993 | 11181993 | 12777993 | 14197993 | 15697993 | 17197993 | 18797993 | 20397993 | 21997993 | 23577993 | 25077993 | 26577993 | 28077993 | 29577993 | 31077993 | 32577993 | 24077993 | 35577993 | 37077993 | 38877993 | 40677993 | 42577993 | 44477993 | 46377993 | 47877993 | 49332993 | 50663793
C2356 | ActualCumCostflow | 138033 | 704480 | 978019 | 1458612 | 2104857 | 3157088 | 3726973 | 4206654 | 4923587 | 5422481 | 6189444 | 7248410 | 8069382 | 9298003 | 10128089 | 11205745 | 11886726 | 12512369 | 13172305 | 14072386 | 15327595 | 16172154 | 17398155 | 19032628 | 20764084 | 22650680 | 24547357 | 26023506 | 27023631 | 29980247

## SubConFinData
ContractNumber | SubContractorName | SubContractNettOrderValue | DesignDevelopment | Package | Site | RecoverableVariations
C2356 | Scaffolding (Seabro) | 1052880 | 0 | -8000 | 187000 | 0
C2356 | Pile attendance & Piling Mats (Erith) | 60010 | 0 | 0 | 0 | 0
C2356 | Demolition (Erith) | 800000 | 0 | 0 | 0 | 473285
C2356 | Groundworks & Frame (GCL) | 10098927 | 222572 | -12813 | 86699 | 124128
C2356 | CFA Piling (Rock & Alluvium) | 356067 | 10028 | 0 | 0 | 10015
C2356 | PCC Floors & stairs | 0 | 0 | 0 | 0 | 0
C2356 | Brickwork (Regents Brkwk) | 1337500 | 1000 | 0 | 54750 | 1500
C2356 | Winter Gardens (Elite) | 702696 | 41244 | 0 | 0 | 0
C2356 | Metal Cladding GF A1/ramp (MBM) | 119501 | 0 | 0 | 0 | 0
C2356 | Ali Rainwaters/Porch Soffits | 62172 | 0 | 0 | 0 | 0
C2356 | Metalwork Balconies (Sapphire/McKeans) | 903414 | 0 | 0 | 0 | 0
C2356 | Blinds (Waverley Blinds) | 75000 | 0 | 0 | 0 | 0
C2356 | Roofing (Accurate) | 926636 | 0 | 14000 | 17500 | 69381
C2356 | Windows Fit only (APW) | 294476 | 0 | 0 | 11200 | 36834
C2356 | Lift (Kone) | 557868 | 0 | 10200 | 0 | 3600
C2356 | Mechanical (I-Mex) | 4770000 | 51000 | 6000 | 2500 | 66790
C2356 | Electrical (East Electrical) | 2159536 | 19654 | 23000 | 750 | 134534
C2356 | BWIC (Gideaward/Kilnbridge) | 27893 | 0 | 0 | 0 | 0
C2356 | Curtain Wallling (Syte Arch) | 72970 | 0 | 0 | 0 | 0
C2356 | Carpentry (Kingsland) | 560395 | 11500 | 0 | 2400 | 12500
C2356 | Landscaping (Fletchers) | 89185 | 0 | 0 | 0 | 0
C2356 | Plastering (Screedforce) | 2964209 | 31250 | 25000 | 10500 | 44000
C2356 | Painting (A & B) | 438170 | 0 | 15750 | 0 | 0
C2356 | Flooring (GCN) | 728220 | 0 | 0 | 0 | 0
C2356 | Basement Cages (Billericay Fencing) | 167639 | 0 | 0 | 0 | 0
C2356 | Timber Fencing | 10548 | 0 | 0 | 0 | 0
C2356 | Car Park Barrier | 5641 | 0 | 0 | 0 | 0
C2356 | Lightning Protection (KG Young/Redpath B) | 28788 | 4458 | 0 | 0 | 0
C2356 | White Goods (DBD) | 396113 | 0 | 0 | 0 | 0
C2356 | Wheelchair Kitchens/white goods | 33000 | 0 | 0 | 0 | 0
C2356 | Lightweight Flooring | 0 | 0 | 0 | 0 | 0
C2356 | Splashbacks | 0 | 0 | 0 | 0 | 0
C2356 | Kitchens (Commodore) | 769666 | 0 | 0 | 0 | 0
C2356 | Play Equipment/Safe Play (Timber Play/RTC) | 56554 | 0 | 0 | 0 | 0
C2356 | Inground pipework District Heating (Burgins) | 8586 | 0 | 0 | -1300 | 0
C2356 | Metsec (Screedforce) | 1566566 | 19300 | 0 | 23400 | 2500
C2356 | Mastic Pointing (Specialist Sealants) | 45000 | 0 | 0 | 0 | 0
C2356 | Metal Prima Doors | 71160 | 0 | 0 | 0 | 0
C2356 | Disabled Lifts (Terry Lifts) | 26000 | 0 | 0 | 0 | 0
C2356 | Structural Screeds (SAK) | 33000 | 0 | 0 | 0 | 0
C2356 | Podium build up/External S106 works | 59500 | 0 | 0 | 0 | 0
C2356 | Basement floor paint | 53361 | 0 | 0 | 0 | 0
C2356 | Ceramics (LLA Brown) | 382953 | 0 | 0 | 0 | 0
C2356 | Site Enabling Works (Corbyn/Dwyer/AD Bly) | 27240 | 0 | 0 | 0 | 30000
C2356 | Tree Surgery (DF Clarke) | 19260 | 0 | 0 | 0 | 0
C2356 | Sheet piling (Fussey) | 334240 | 0 | -81794 | 0 | 68598
C2356 | Photovoltaics (Eco Team) | 32400 | 0 | 0 | 0 | 0
C2356 | GW risk | 0 | 0 | 0 | 0 | 0
C2356 | Waterproofing to Slabs (Southern Mastics) | 137238 | 3000 | 0 | 0 | 0
C2356 | Metalwork (TAD) | 395000 | 0 | 0 | 0 | 0

## HSData
ContractNumber | time axis 2013-01-01 to 2017-03-01
C2356 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 42 | 49 | 42 | 43 | 41.5 | 37 | 43.5 | 33 | 41 | 43 | 42.5 | 43.2 | 44.64 | 39.36 | 39.912 | 42 | 87.5 | 87.5 | 72 | 66 | 66
C2356 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 87.5 | 81.6667 | 87.5 | 89.5833 | 86.4583 | 77.0833 | 90.625 | 68.75 | 85.4167 | 89.5833 | 88.5417 | 90 | 93 | 82 | 83.15 | 87.5 | 87.5 | 87.5 | 93.51 | 92 | 92

## TradeAccidents
ContractNumber | Asbestos | Brickwork | Carpenty | Cladding | Cleaning | Demolition | Electrical | Fencing | Flooring | Forklift | Frame | Glazing | Groundwork | Insulation | Labourer | Landscaping | Lifts | LightningProtection | Management | Mastic | Mechanical | MetalWork | PaintingDec | PestControl | Piling | Plastering | Plumbing | Render | Roofing | Scaffolding | Steelwork | Tiling | TreeSurgery | WaterProofing | Windows
C2356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0

## AccidentReport
ContractNumber | Date | Trade | Type | LostDays | Riddor
C2356 | 12.02.16 | Labourer | Foot | 0 | 1
C2356 | 26.07.16 | Scaffolder | Hand | 0 | 1
C2356 | 26.07.16 | Scaffolder | Shoulder | 0 | 0
C2356 | 22.09.16 | Labourer | Eye | 1 | 0
C2356 | 16.09.16 | Labourer | Ankle | 1 | 0
C2356 | 23.09.16 | Labourer | Hand | 0 | 0

## MaterialOrdersCategories
ContractNumber | partSite | wholeSite | replacement
C2356 | 2 | 1 | 4

## MaterialOrdersType
ContractNumber | clientChange | theft | waste | garage
C2356 | 2 | 1 | 3 | 5

## TypeAccidents
ContractNumber | Abdomen | Arms | Back | Burns | Chest | Eyes | Face | Feet | Hands | Head | Jaw | Legs | Muscular | Neck | Pelvis | Penis | Shoulder | Skeletal
C2356 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0